## Work Log
|  | 32.25 |  |  | <- Totals
date | time | hours | work | notes
|  | 10 | preliminary setup… | looking at various templates, new development techniques. Started index page. Searching for content.
aug 21 2017 | 9:15-10:30 pm | 1.25 | modulated index (head, top, footer). Started historique (about us)
aug 22 2017 | 8:15-9:15 pm | 1 |  | Thought about a local php server for development but it will just take too much time and hassle. Deciding to develop all look and feel first and show to gerry before developing all functionality the old way directly on the server through filezilla
aug 23 2017 | 9:00-10:30 pm | 1.5 | Notes for email to gerry. insert content for history page (html_build, video, history blurb, image editing, image searching)
aug 25 2017 | 7:30-8:30 pm | 1 | fixing problem with youtube player in historique page. Inputting/searching for images/content. Starting rooms page.
aug 26 2017 | 10:00-10:30 am | 0.5 | organization of top menu bar. Started rooms page.
| 1:15-3:15 PM | 2 | fixed image resizing problem for all the rooms images on the rooms page. Finished rooms page. Initial test upload.
| 6:50-7:20 PM | 0.5 | Collected image content from google
aug 27 2017 | 11:00-12:15 AM | 1.25 | Finishing touches on the top menu. Finished Contact page, Gallery Page. Final notes for Gerry for phase 1. Uploading site.
| 1:15-1:30 PM | 0.25 | verification of live version, email to gerry
Phase 2
date | time | hours | work | notes
Aug 28 2017 | 9:15-10:00 PM | 0.75 | XAMPP almost working with gulp for local php development
Aug 30 2017 | 8:30:00-9:00 PM | 0.5 | gulp is connected to XAMPP for local php development | Will now be able to develop php functionality on my local machine.
Sept 2 2017 | 9:45-10:45 AM | 1 | started implementing fixes Gerry asked for, started implementing functionality.
| (On and off) | 5 | Correctly configured XAMPP, mysql problems…
|  | 3 | cross page functionality using localstorage
Sept 6 2017 | 8:15-9:00 PM | 0.75 | Continuing cross page functionality using localstorage
Sept 9 2017 | 1:00-2:15 PM | 1.25 | More cross page functionality, fixed video player. Best rooms.
Sept 12 2017 | 8:45-9:30 PM | 0.75 | Added requested front page text, working on events API.